## 📅 Project Timeline
ZOHO ↔ DAYSMART DATA MIGRATION PROJECT — Full Work Log
April 2026 · Contact Data Hygiene, Cross-Reference, ZeroBounce Verification & HubSpot/Scheduler Import Preparation
# | Phase | Task Completed | Key Outputs | Records Affected | Status
1 | Phase 1 Data Generation | Generated 21,000 mock contact records using Python Faker library | zoho_crm_contacts.csv (13,000) daysmart_contacts.csv (8,000) | 21,000 contacts | ✅ Done
2 | Phase 1 Data Generation | Generated 51,464 DaySmart appointment history records | daysmart_appointment_history.csv | 51,464 appt rows | ✅ Done
3 | Phase 2 7-Year Rule | SQL: MAX(Last_Appointment_Date) per contact in SQLite | max_appointment_date per contact | 8,000 DaySmart | ✅ Done
4 | Phase 2 7-Year Rule | Applied 7-Year Classification Rule (cutoff 2019-01-01) | daysmart_classified.csv LIVE: 5,214 ¦ ARCHIVE: 2,786 | 8,000 contacts | ✅ Done
5 | Phase 2 7-Year Rule | Generated Data Health Report Excel (4 sheets + charts) | DaySmart_Data_Health_Report.xlsx | 8,000 contacts | ✅ Done
6 | Phase 3 Cross-Reference | Email cross-reference: Zoho ↔ DaySmart by email address | 1,193 matched ¦ 10,866 Zoho-only 6,807 DaySmart-only | 21,000 contacts | ✅ Done
7 | Phase 3 Cross-Reference | Rescue Logic: Bounced Zoho emails matched via Full_Name to DaySmart | rescued_contacts.csv (373 rescued) 667 unrescuable | 1,040 bounced | ✅ Done
8 | Phase 3 Cross-Reference | Deduplication (DaySmart = Source of Truth) | master_contact_list.csv 18,866 unique records | 21,000 → 18,866 | ✅ Done
9 | Phase 3 Cross-Reference | Generated CrossRef Data Health Report (6 sheets + charts) | CrossRef_DataHealth_Report.xlsx | 18,866 records | ✅ Done
10 | Phase 4 ZeroBounce | Simulated ZeroBounce verification on all 18,866 master records | Valid:14,162 ¦ Catch-all:1,488 Invalid:1,217 ¦ Spamtrap:340 | 18,866 records | ✅ Done
11 | Phase 4 ZeroBounce | Applied Clinical Exception Rule (invalid email + DaySmart client) | Email nulled, Name+Phone kept 9 records | 9 contacts | ✅ Done
12 | Phase 4 ZeroBounce | Applied Prospect Rule (invalid email + no DaySmart booking) | 1,792 records deleted | 1,792 deleted | ✅ Done
13 | Phase 4 ZeroBounce | Applied Unsubscribe Rule (Email_Opt_In = No) | 3,983 contacts suppressed | 3,983 flagged | ✅ Done
14 | Phase 4 ZeroBounce | Scored & ranked Top 1,000 Marketing Contacts | top1000_marketing.csv Score: Opens(20)+Clicks(20)+Recency(25)+Revenue(15)+Visits(10)+ZB(10) | 12,717 eligible | ✅ Done
15 | Phase 4 ZeroBounce | Generated ZB+Rules+Marketing Excel Report (6 sheets) | ZB_Rules_Marketing_Report.xlsx | 18,866 records | ✅ Done
16 | Phase 5 Export Files | File A: HubSpot CRM Import CSV (standard headers, semicolon multi-select) | FileA_HubSpot_Import.csv 13,091 records ¦ Zoho→HubSpot field mapping | 13,091 records | ✅ Done
17 | Phase 5 Export Files | File B: New Scheduler Contacts — LIVE only (2019–2026) | FileB_Scheduler_Contacts_LIVE.csv 16,080 records | 16,080 records | ✅ Done
18 | Phase 5 Export Files | File C: Scheduler Appointment History — LIVE, mapped by contact_id FK | FileC_Scheduler_ApptHistory_LIVE.csv 23,328 rows ¦ 5,010 unique contacts | 23,328 appt rows | ✅ Done
19 | Phase 5 Export Files | File D: Archive CSV — pre-2019 history + invalid prospects, flattened | FileD_Archive.csv 4,578 records ¦ 1 row per contact | 4,578 contacts | ✅ Done
20 | Phase 5 Export Files | Export Manifest Excel with field mapping dictionary (5 sheets) | ExportManifest_AllFiles.xlsx Zoho Last_Open_Date → hs_last_open_date | All files | ✅ Done
21 | Phase 6 Power BI | Power BI DAX measures & calculation guide | PowerBI_Calculations.xlsx (this file) | All data | 🔄 Next
PROJECT SUMMARY: 21,000 raw contacts → 18,866 deduped master → 17,074 active → 13,091 HubSpot-ready → 1,000 top marketing + 4 import files + 5 Excel reports

## ⚡ Power BI DAX Measures
POWER BI — DAX MEASURES & CALCULATIONS
Source tables: FileA (HubSpot) · FileB (Scheduler Contacts) · FileC (Appt History) · FileD (Archive)
Category | Measure Name | DAX Formula | Source Table | Recommended Visual
Contact Volume | Total Contacts | Total Contacts = COUNTROWS(FileB_Scheduler_Contacts) | FileB | Card
Contact Volume | LIVE Contacts | LIVE Contacts = CALCULATE(COUNTROWS(FileB), FileB[data_status]="LIVE") | FileB | Card
Contact Volume | ARCHIVE Contacts | ARCHIVE Contacts = CALCULATE(COUNTROWS(FileB), FileB[data_status]="ARCHIVE") | FileB | Card
Contact Volume | LIVE % | LIVE % = DIVIDE([LIVE Contacts],[Total Contacts],0) | FileB | Card (%)
Contact Volume | Contacts by Year | Contacts by Year = CALCULATE(COUNTROWS(FileB), USERELATIONSHIP(FileB[last_appt_year], DimDate[Year])) | FileB + DimDate | Bar Chart
Revenue & Value | Total Lifetime Revenue | Total Revenue = SUM(FileB_Scheduler_Contacts[lifetime_spend]) | FileB | Card ($)
Revenue & Value | Avg Revenue per Contact | Avg Revenue = DIVIDE(SUM(FileB[lifetime_spend]), COUNTROWS(FileB), 0) | FileB | Card ($)
Revenue & Value | Revenue LIVE vs ARCHIVE | Rev LIVE = CALCULATE(SUM(FileB[lifetime_spend]), FileB[data_status]="LIVE") Rev ARCHIVE = CALCULATE(SUM(FileB[lifetime_spend]), FileB[data_status]="ARCHIVE") | FileB | Clustered Bar
Revenue & Value | Top Service Revenue | Service Revenue = CALCULATE(SUM(FileC[amount_usd]), ALLEXCEPT(FileC, FileC[service])) | FileC | Bar Chart
Revenue & Value | Monthly Revenue Trend | Monthly Revenue = CALCULATE(SUM(FileC[amount_usd]), DATESMTD(FileC[appointment_date])) | FileC + DimDate | Line Chart
Appointment Metrics | Total Appointments | Total Appts = COUNTROWS(FileC_Scheduler_ApptHistory) | FileC | Card
Appointment Metrics | Completed Appointments | Completed = CALCULATE(COUNTROWS(FileC), FileC[status]="Completed") | FileC | Card
Appointment Metrics | No-Show Rate | No-Show Rate = DIVIDE( CALCULATE(COUNTROWS(FileC), FileC[status]="No-Show"), COUNTROWS(FileC), 0) | FileC | Card (%)
Appointment Metrics | Avg Appointments per Contact | Avg Appts = DIVIDE([Total Appts],[Total Contacts],0) | FileC / FileB | Card
Appointment Metrics | Appointments by Month | Appts by Month = CALCULATE(COUNTROWS(FileC), DATESMTD(FileC[appointment_date])) | FileC | Line Chart
Email & Engagement | Email Deliverability Rate | Deliverability = DIVIDE( CALCULATE(COUNTROWS(FileA), FileA[zerobounce_status]="valid"), COUNTROWS(FileA), 0) | FileA | Gauge / Card (%)
Email & Engagement | Total Email Opens | Total Opens = SUM(FileA_HubSpot_Import[hs_email_open]) | FileA | Card
Email & Engagement | Avg Open Rate per Contact | Avg Opens = DIVIDE(SUM(FileA[hs_email_open]), COUNTROWS(FileA), 0) | FileA | Card
Email & Engagement | Click-to-Open Rate | CTOR = DIVIDE(SUM(FileA[hs_email_click]), SUM(FileA[hs_email_open]), 0) | FileA | Card (%)
Email & Engagement | Unsubscribe Rate | Unsub Rate = DIVIDE( CALCULATE(COUNTROWS(FileA), FileA[unsubscribed_from_all_email]=TRUE), COUNTROWS(FileA), 0) | FileA | Card (%)
Data Quality | ZeroBounce Status Breakdown | ZB Valid = CALCULATE(COUNTROWS(FileA), FileA[zerobounce_status]="valid") ZB Invalid = CALCULATE(COUNTROWS(FileA), FileA[zerobounce_status]="invalid") ZB Spamtrap = CALCULATE(COUNTROWS(FileA), FileA[zerobounce_status]="spamtrap") | FileA | Donut Chart
Data Quality | Clinical Exceptions | Clinical = CALCULATE(COUNTROWS(FileA), FileA[data_rule_applied]="Clinical Exception") | FileA | Card
Data Quality | Prospects Deleted | Deleted = CALCULATE(COUNTROWS(FileA), FileA[data_rule_applied]="Prospect Rule") | FileA | Card
Data Quality | Data Completeness Score | Completeness = DIVIDE( CALCULATE(COUNTROWS(FileB), FileB[email]<>""), COUNTROWS(FileB), 0) | FileB | Gauge (%)
Marketing Top 1000 | Top 1K — Avg Marketing Score | Top1K Score = CALCULATE(AVERAGE(FileA[marketing_score]), TOPN(1000, FileA, FileA[marketing_score], DESC)) | FileA | Card
Marketing Top 1000 | Top 1K — Lifecycle Split | Top1K Customers = CALCULATE( COUNTROWS(FileA), FileA[lifecyclestage]="customer", TOPN(1000, FileA, FileA[marketing_score], DESC)) | FileA | Pie / Donut
Marketing Top 1000 | Score Scatter Plot | X Axis = Email_Opens, Y Axis = Marketing_Score Size = lifetime_value Color = lifecyclestage | FileA | Scatter Chart
Archive Analysis | Archive vs LIVE Revenue Gap | Rev Gap = [Rev LIVE] - [Rev ARCHIVE] | FileB | Card ($)
Archive Analysis | Archive Contacts by Last Year | Archive by Year = CALCULATE(COUNTROWS(FileD), ALLEXCEPT(FileD, FileD[archive_last_appt])) | FileD | Bar Chart
Archive Analysis | Avg Years Since Archive Contact | Avg Archive Age = AVERAGEX(FileD, DATEDIFF(DATE(FileD[last_known_appointment]),TODAY(),YEAR)) | FileD | Card

## 📊 Power BI Dashboard Plan
POWER BI — 5-PAGE DASHBOARD LAYOUT PLAN (Chart Fields, Axes & DAX)
Tables: FileA = HubSpot · FileB = Scheduler Contacts LIVE · FileC = Appt History LIVE · FileD = Archive
Page | Visual Type | DAX Measure / Field | X Axis | Y Axis | Legend / Color | Filter / Slicer | Notes
Page 1 — Contact — Overview
Page 1 Contact Overview | KPI Card × 4 | [Total Contacts] [LIVE Contacts] [ARCHIVE Contacts] [LIVE %] | — | — | — | — | 4টি আলাদা Card visual। Format → Callout value-এ % format দিন LIVE %-এর জন্য
Page 1 Contact Overview | Bar Chart (Clustered Column) | FileB[last_appt_year] COUNTROWS(FileB) | FileB[last_appt_year] (X Axis — Categorical) | [Total Contacts] (Y Axis — Value) | FileB[data_status] (Legend — LIVE/ARCHIVE color) | Slicer: FileB[data_status] | Sort X axis ascending (2019→2026). Color: LIVE=green, ARCHIVE=red
Page 1 Contact Overview | Donut Chart | FileB[data_status] COUNTROWS(FileB) | — | COUNTROWS(FileB) (Values) | FileB[data_status] (Legend) | — | Detail labels-এ % দেখান। 2 slice: LIVE / ARCHIVE
Page 1 Contact Overview | Slicer | FileB[data_status] FileA[zerobounce_status] | — | — | — | — | 2টি আলাদা Slicer। Style → Dropdown বা List
Page 2 — Revenue & — Appointments
Page 2 Revenue & Appointments | KPI Card × 4 | [Total Revenue] [Avg Revenue] [Total Appts] [No-Show Rate] | — | — | — | — | Total Revenue → $#,##0 format। No-Show Rate → % format
Page 2 Revenue & Appointments | Line Chart | DimDate[MonthName] [Monthly Revenue] (DATESMTD) | DimDate[MonthName] (X Axis — time axis) | [Monthly Revenue] (Y Axis — $) | — | DimDate Slicer: Year filter | X axis sort করুন: MonthNum ascending। Markers on দিন।
Page 2 Revenue & Appointments | Bar Chart (Clustered Column) | FileC[service] SUM(FileC[amount_usd]) | FileC[service] (X Axis — service name) | SUM(FileC[amount_usd]) (Y Axis — $ revenue) | — | Slicer: FileC[status] | Top N filter দিন: Top 10 services by revenue
Page 2 Revenue & Appointments | Clustered Bar (Horizontal) | [Total Revenue] split by FileB[data_status] | FileB[data_status] (Y Axis — LIVE/ARCHIVE) | [Total Revenue] (X Axis — $ value) | FileB[data_status] (Color) | — | Horizontal bar দিন — 2টি bar পাশাপাশি। Revenue gap clearly দেখা যাবে
Page 2 Revenue & Appointments | Gauge | [No-Show Rate] | — | [No-Show Rate] (Value) | — | — | Min=0, Max=1, Target=0.10 (10%). Color: green if <10%, red if >10%
Page 3 — Email Health — & ZeroBounce
Page 3 Email Health & ZeroBounce | KPI Card × 5 | SUM(FileA[hs_email_open]) SUM(FileA[hs_email_click]) [CTOR] [Deliverability Rate] [Unsub Rate] | — | — | — | — | CTOR ও Deliverability → % format। Opens/Clicks → whole number
Page 3 Email Health & ZeroBounce | Donut Chart | FileA[zerobounce_status] COUNTROWS(FileA) | — | COUNTROWS(FileA) (Values) | FileA[zerobounce_status] (Legend — 7 categories) | — | 7 slice: valid/invalid/catch-all/unknown/spamtrap/abuse/do_not_mail। % label দিন
Page 3 Email Health & ZeroBounce | Bar Chart (Clustered Column) | FileA[data_rule_applied] COUNTROWS(FileA) | FileA[data_rule_applied] (X Axis — rule name) | COUNTROWS(FileA) (Y Axis — count) | FileA[data_rule_applied] (Color per rule) | — | 5 bars: Pass / Clinical Exception / Prospect Rule / Unsubscribe / Do Not Mail
Page 3 Email Health & ZeroBounce | Gauge | [Data Completeness] | — | [Data Completeness] (Value) | — | — | Min=0, Max=1, Target=0.95 (95%). Shows % contacts with valid email
Page 4 — Top 1,000 — Marketing
Page 4 Top 1,000 Marketing | KPI Card × 4 | [Top1K Avg Score] COUNT customers COUNT leads [Avg Revenue] | — | — | — | — | Top1K Avg Score → 1 decimal। Filter page to marketing_score TOP 1000
Page 4 Top 1,000 Marketing | Scatter Chart | FileA[hs_email_open] FileA[marketing_score] FileA[lifetime_value] FileA[lifecyclestage] | FileA[hs_email_open] (X Axis — opens count) | FileA[marketing_score] (Y Axis — score 0-100) | FileA[lifecyclestage] (Legend — customer/lead color) | Slicer: FileA[lifecyclestage] | Size = FileA[lifetime_value]। Top 1000 filter দিন। Zoom slider on করুন
Page 4 Top 1,000 Marketing | Bar Chart (Clustered Column) | Score band column (60-65/65-70/70-75/75-80/80+) COUNTROWS | Score Band (X Axis — range label) | COUNTROWS(FileA) (Y Axis — contact count) | — | Slicer: FileA[lifecyclestage] | Score band = calculated column: IF(score>=80,"80+",IF(score>=75,"75-80",...))
Page 4 Top 1,000 Marketing | Table Visual | firstname & lastname email marketing_score lifecyclestage hs_email_open hs_email_click lifetime_value zerobounce_status | — | — | — | Top N filter: Top 50 by marketing_score | Sort by marketing_score DESC। Conditional formatting: score column → color scale
Page 4 Top 1,000 Marketing | Slicer × 3 | FileA[lifecyclestage] FileA[zerobounce_status] FileA[data_rule_applied] | — | — | — | — | 3টি আলাদা Slicer — page cross-filter করবে সব visual-এ
Page 5 — Archive & — Data Quality
Page 5 Archive & Data Quality | KPI Card × 4 | COUNTROWS(FileD) [ARCHIVE Contacts] COUNTROWS(Deleted Prospects) [Archive Revenue] | — | — | — | — | Archive Revenue = SUM(FileD[archive_total_spent])
Page 5 Archive & Data Quality | Bar Chart (Clustered Column) | FileD[last_known_appointment] COUNTROWS(FileD) | YEAR(FileD [last_known_appointment]) (X Axis — year) | COUNTROWS(FileD) (Y Axis — contact count) | FileD[reason_archived] (Color — reason) | Slicer: FileD[reason_archived] | X axis = calculated column: Archive Year = YEAR(FileD[last_known_appointment])
Page 5 Archive & Data Quality | Donut Chart | FileD[reason_archived] COUNTROWS(FileD) | — | COUNTROWS(FileD) (Values) | FileD[reason_archived] (Legend) | — | 2 slices: Pre-2019 last appointment / Invalid email — no booking
Page 5 Archive & Data Quality | KPI Card | [Avg Archive Age] | — | [Avg Archive Age] (Value — years) | — | — | AVERAGEX(FileD, DATEDIFF(FileD[last_known_appointment], TODAY(), YEAR))
Page 5 Archive & Data Quality | Table Visual | master_id · full_name · email last_known_appointment archive_last_appt archive_total_spent archive_last_service reason_archived zerobounce_status | — | — | — | Slicer: FileD[reason_archived] FileD[zerobounce_status] | Conditional format: reason_archived column। Sort by last_known_appointment DESC
COLUMN COLOR GUIDE: Page (dark bg) · Visual Type (colored text) · Measure/Field (blue mono) · X Axis (purple) · Y Axis (green) · Legend/Color (orange) · Filter/Slicer (grey) · Notes (italic)

## 🔗 Data Model
POWER BI DATA MODEL — Table Relationships
From Table | To Table | Join Type | Key Fields | Cardinality
FileA_HubSpot | FileB_Scheduler_Contacts | LEFT JOIN | email = email | Many-to-One
FileB_Scheduler_Contacts | FileC_Appt_History | ONE-to-MANY | contact_id = contact_id | 1 contact → many appts
FileB_Scheduler_Contacts | FileC_Appt_History | ONE-to-MANY | contact_id = contact_id | 2 contact → many appts
FileA_HubSpot | DimDate | MANY-to-One | last_appointment_date = Date | For time intelligence
FileB_Scheduler_Contacts | FileD_Archive | UNION (no join) | — | Same schema, combined in view
FileA_HubSpot | FileD_Archive | LEFT JOIN | master_id = master_id | Audit trail linkage
DimDate | DimDate | — | Year · Month · Quarter · Week | Standard date dimension
DimDate = standard date dimension table. Create in Power BI: Modeling → New Table → DimDate = CALENDARAUTO(). Add Year/Month/Quarter/WeekNum calculated columns.

## 📁 All Output Files
ALL PROJECT OUTPUT FILES — Complete Inventory
Filename | Type | Records | Purpose | Use In Power BI
zoho_crm_contacts.csv | CSV | 13,000 | Original Zoho CRM mock dataset | Raw source (optional)
daysmart_contacts.csv | CSV | 8,000 | Original DaySmart mock dataset | Raw source (optional)
daysmart_appointment_history.csv | CSV | 51,464 | Full appointment history | FileC source data
daysmart_classified.csv | CSV | 8,000 | 7-Year LIVE/ARCHIVE classification | Supplementary
DaySmart_Data_Health_Report.xlsx | Excel | 8,000 | Phase 2 health report (4 sheets + charts) | Reference / Stakeholder
master_contact_list.csv | CSV | 18,866 | Deduped master (pre-rules) | Supplementary
rescued_contacts.csv | CSV | 373 | Bounced → rescued contacts | Reference
zoho_only_prospects.csv | CSV | 10,866 | Zoho-only never-booked prospects | Reference
CrossRef_DataHealth_Report.xlsx | Excel | 18,866 | Phase 3 cross-reference report (6 sheets) | Stakeholder
master_rules_applied.csv | CSV | 18,866 | Full master with ZB + rules applied | Import to Power BI
active_contacts.csv | CSV | 17,074 | Post-rule active contacts | Import to Power BI
deleted_prospects.csv | CSV | 1,792 | Audit log of deleted records | Reference / Audit
top1000_marketing.csv | CSV | 1,000 | Top 1,000 scored marketing contacts | ★ Import to Power BI
ZB_Rules_Marketing_Report.xlsx | Excel | 18,866 | Phase 4 report (6 sheets + charts) | Stakeholder
FileA_HubSpot_Import.csv | CSV | 13,091 | ★ HubSpot CRM import file | ★ Import to Power BI (FileA)
FileB_Scheduler_Contacts_LIVE.csv | CSV | 16,080 | ★ Scheduler contacts (LIVE) | ★ Import to Power BI (FileB)
FileC_Scheduler_ApptHistory_LIVE.csv | CSV | 23,328 | ★ Appointment history (LIVE, FK mapped) | ★ Import to Power BI (FileC)
FileD_Archive.csv | CSV | 4,578 | ★ Archive contacts + history flattened | ★ Import to Power BI (FileD)
ExportManifest_AllFiles.xlsx | Excel | All | Field mapping dictionary (5 sheets) | Reference
PowerBI_Calculations.xlsx | Excel | — | ★ This file — DAX measures + dashboard plan | ★ Build Power BI from this